## Mutual Action Plan
MUTUAL ACTION PLAN
Shared roadmap to a successful partnership
DEAL OVERVIEW
Account: | [Company Name] |  |  | Our Sponsor: | [Your Executive Sponsor]
Project: | [Project / Initiative Name] |  |  | Their Sponsor: | [Customer Champion / EB]
Objective: | [Shared business outcome] |  |  | Target Go-Live: | 2026-10-01
↑ Edit the Target Go-Live date above. All due dates below recalculate automatically.
ACTION ITEMS
# | Phase | Action Item | Owner (Us) | Owner (Them) | Days Before Go-Live | Due Date | Status | Notes / Blockers
1 | Discovery & Alignment | Confirm business objectives and success criteria | AE / SC | VP Sales | 80 | 2026-07-13 | Complete | Aligned on 3 KPIs
2 |  | Map decision-making process and stakeholders | AE | Champion | 75 | 2026-07-18 | Complete
3 |  | Share security and compliance documentation | SC | IT / Security | 70 | 2026-07-23 | In Progress | Awaiting SOC 2 review
4 |  | Complete technical requirements questionnaire | SC | Solutions Architect | 65 | 2026-07-28 | Not Started
5 | Evaluation & Proof of Value | Define POC scope and success metrics | AE / SC | Champion | 60 | 2026-08-02 | In Progress | Draft shared, awaiting feedback
6 |  | Provision sandbox / trial environment | SC | IT Admin | 55 | 2026-08-07 | Not Started
7 |  | Conduct POC kickoff and training session | SC | Project Lead | 50 | 2026-08-12 | Not Started
8 |  | Execute POC against agreed success criteria | SC / CSM | End Users | 35 | 2026-08-27 | Not Started | 2-week evaluation window
9 |  | Review POC results and document findings | AE / SC | Champion / EB | 30 | 2026-09-01 | Not Started
10 | Business Case & Approval | Build joint ROI / business case | AE | Champion | 28 | 2026-09-03 | Not Started
11 |  | Present business case to Economic Buyer | AE | Champion / EB | 24 | 2026-09-07 | Not Started
12 |  | Complete procurement and legal review | AE / Legal | Procurement | 16 | 2026-09-15 | Not Started
13 |  | Finalize contract terms and pricing | AE | Procurement / EB | 10 | 2026-09-21 | Not Started
14 | Close & Launch | Execute agreement | AE / Legal | Legal / EB | 7 | 2026-09-24 | Not Started
15 |  | Kick off implementation and onboarding | CSM / SC | Project Lead | 3 | 2026-09-28 | Not Started
16 |  | Conduct end-user training | CSM | Enablement Lead | 1 | 2026-09-30 | Not Started
17 |  | Go-live and first value review | CSM / AE | Champion / EB | 0 | 2026-10-01 | Not Started
STATUS KEY |  | Complete | In Progress | Not Started | At Risk | Blocked
HOW DATES WORK: Each action has a "Days Before Go-Live" value. The Due Date = Target Go-Live minus that number. Change the go-live date (F7) or any offset to update automatically.
Formulas:
Due Date = F7-[Days Before Go-Live]